## To Do
Added at | Type | Progress | Priority | Description | Mark
2022-08-25 | New (needed) | Finished |  | PatternRectangle (as UserControl)
2022-08-25 | Improvement | Finished |  | Option to select show MBT_0 or MBT_1 (zero or 1-based)
2022-08-26 | Bugfix | Finished |  | Measure Strip is not shown correctly when application starts (needs first as scale up + scale down)
2022-08-25 | Improvement | Finished |  | Stop SequencerPlay at end of Composition
2022-08-25 | Improvement | Finished |  | Option to ShowSequencerPosition
2022-08-25 | Improvement | Finished |  | Option to ScrollIntoView when Playing
2022-08-25 | New (needed) | Finished |  | Play Pattern in PatternStore (Drum/Voice)
2022-08-25 | New (needed) | Finished |  | Delete Pattern in Track
2022-08-25 | New (needed) | Finished |  | Move Pattern in Track - with TextDialog, graphical
2022-08-25 | New (needed) | Finished |  | Size Pattern in Track - with TextDialog, graphical
2022-08-25 | New (needed) | Finished |  | Copy / Paste PatternRectangle
2022-09-14 | New (needed) | Finished |  | Composition.IsEqual for comparing Composition in Memory and Composition on Disk, for askig "Save changes ?" at Application close
2022-08-25 | New (needed) | Finished |  | Debug Tab
2022-08-25 | New (needed) | Finished |  | Debug: Button to show current pointers
2022-09-30 | New (needed) | Finished |  | Function to change Composition Length
2022-09-30 | New (needed) | Finished |  | Function to create New Composition
2022-08-25 | New (needed) | Finished |  | Play Pattern in Track
2022-08-25 | Improvement | Finished |  | Loop play (left / right in Measure Strip)
2022-08-25 | New (nice to have) | Finished |  | Debug: Events at output counter (MidiOutShortMsg_Counter)
2022-12-24 | Improvement | Finished |  | Audition: Player schould increase StartOffset instead of StartTime when Looping --> now using PlayTrack for Composition AND Audition Play
2022-08-25 | Improvement | Finished |  | Voice Param to Output
2022-08-25 | Improvement | Finished |  | Voice Test Play --> Tap Button
2022-08-25 | New (nice to have) | Finished |  | Control for RTZ Back Stop Play Forward (Tool Window) --> Remote-Control
2022-08-25 | New (needed) | Pending | Normal | Edit Pattern (Voice)
2022-08-25 | New (needed) | Pending | Normal | Edit Pattern (Drums)
2022-12-22 | New (in far future) | Pending | Normal | Main Window: Tab for Loop-Player (Live Player). Multi- Track/Voice up to 5 Patterns per Track, user can set Timed changes on each track
2022-08-25 | New (needed) | Pending | Normal | Cut/Paste PatternRectangle (in addition to Copy / Paste)
2022-08-25 | New (needed) | Pending | Normal | Section Strip
2022-08-25 | Improvement | Pending | Normal | improve Audition: always running, synchronized with SequencerTime, stopAuditionPlay
2022-08-25 | New (needed) | Pending | Normal | Sections defining / Playing
2022-08-25 | New (nice to have) | Pending | Normal | option to turn UI off (run Player only)
2022-08-25 | New (nice to have) | Pending | Normal | option to turn Audition processing off (?)
2022-08-25 | New (nice to have) | Pending | Normal | counter for Notes played from Sequencer
2022-08-25 | New (nice to have) | Pending | Normal | counter for notes played from Audition
2022-08-25 | Improvement | Pending | Normal | PatternStore: play Loop
2022-09-02 | Improvement | Pending | Normal | Property ScaleX for Track. In Module1 for easier access instead of SequencerPanel1.TracksHeader.ScaleX
2022-09-02 | Bugfix | Pending | Normal | Scrollbar (MasterScroll) is not set to current value when the application starts
2022-09-05 | Improvement | Pending | Normal | StatusBar Position of Mouse on TrackCanvas. Empty when Mouse leaves TrackCanvas
2022-09-14 | New (needed) | Pending | Normal | adding a new Project "Tools" for UserControls: ChordPlay (Test), Pattern edit, Midi record, MidiFile Import. This UserControls can be placed into Windows or Tabs in the SQ1 Main Window
2022-09-14 | New (needed) | Pending | Normal | include SectionList in Composition
2022-09-14 | New (needed) | Pending | Normal | make Mute functional in Voice and Track
2022-12-29 | Improvement | Pending | Normal | More than 1 Proc for Play_Pattern (with Voice, one-time,..
2022-12-29 | Improvement | Pending | Normal | Initialisation and Midi-Init after Composition was loaded
2022-08-25 | New (nice to have) | Pending | Low | Ribbon (?)
2022-08-25 | New (needed) | Pending | Low | Marker Strip
2022-08-25 | New (nice to have) | Pending | Low | Selectable Position: M:B:T B:T T
2022-08-25 | Improvement | Pending | Low | clear Debug MidiOut Datat
2022-08-25 | New (nice to have) | Pending | Low | Controller recording
2022-08-25 | New (nice to have) | Pending | Low | load Midi-File with Dialog to select Tracks, MetaEvent selecting,..
2022-08-25 | New (nice to have) | Pending | Low | save as Midi-File
2022-09-02 | Improvement | Pending | Low | Forward / Rewind Button for Sequencer Position (when Sequencer.IsRunning = FALSE
2022-09-14 | New (nice to have) | Pending | Low | user definable Colors for each PatternRectangle (User can optionally give selected PatternRectangles different colors)
2022-08-25 | New (nice to have) | Later | Low | Debug: counter for Notes processed
2022-08-25 | New (nice to have) | Later | Low | Debug: Note off processed counter
2022-08-25 | New (nice to have) | Later | Low | Debug: Direct event out counter
2022-08-25 | New (nice to have) | Later | Low | Debug: Note events at output counter
2022-08-26 | New (in far future) | Later | Low | Support for Synthesizer Sysx Messages, specific Sythesizer Voicelists,..
2022-08-29 | New (nice to have) | Later | Low | List+ListPtr for SingleEvents (per Track)
2022-09-02 | New (nice to have) | Later | Low | Composition IsEqual to test if there were changes before Application closes (save Dialog if not equal).
2022-09-02 | New (nice to have) | Later | Low | Store settings (Positions, sizes,..) in SequencerUI to File
2022-09-06 | New (in far future) | Later | Low | Maps for UserDefined Tables like VoiceMaps, DrumMaps,...
2022-09-30 | Improvement | Later | Low | Sequencer.Play_Pattern (Audition): copy desired Voice to Audition and send Voice/Param-changes to the Output
2022-09-30 | New (needed) | Later | Low | PatternRectangle: Function for DividePattern (make 2 Patterns from 1 Pattern)
2022-09-30 | New (nice to have) | Later | Low | Help System for Application
2022-10-31 | New (nice to have) | Later | Low | Transpose Functionality in Track/Panel and/or Voice
2022-10-31 | Improvement | Later | Low | Function to remove Pattern from PatternStore / do not Load duplicate
2022-10-31 | Improvement | Later | Low | Group and Description column in PatternStore
2022-10-31 | Improvement | Later | Low | VoicePanel: Menu for selecting Voice by Name
2022-12-16 | New (nice to have) | Later | Low | Pattern edit: Figures(Phrases) preset and user definable
2022-12-22 | New (in far future) | Later | Low | Sequencer: provide Elapsed-Milliseconds Readonly Property for non-BPM related Durations
2022-12-31 | Bugfix | Pending | Normal | Pattern play: not all Notes were played (Audition) when SequencerPosition > 0 --> CopyPattern and Reset StartPosition, StartOffset, EventListPtr
2022-12-31 | Bugfix | Pending | Normal | Need 'ask for save' at exit when a new Composition was created --- Seems it is saved, but without asking or notify
2023-02-02 | New (needed) | Pending | Normal | add immediatePlay to Audiotion. For playing pattern when the duration is undetermined. Patterns are hold in a List, have ID (for stopping), VoiceNumber and start- and ending type (immediate, beat aligned,..) Pattern which are not set to Loop are removed automatically at the end of the duration or when Audition stops
2023-02-03 | New (nice to have) | Later | Low | MidiFile Import: add a graphical grid, 1 cell represents 1 Beat, the cell is filled with a brush when there are 1 or more events within this beat. This will help getting a better overview per track, sometimes only a little part of a track is really used. User maybe just wants to cut out a little part of a track. This will also help detecting files with a few empty beats at the end.
2023-02-03 | New (nice to have) | Later | Low | Pattern import from MidiFile: A part of a track can be marked and saved as pattern to PatternStore or to disk. Usually start and end at beat mark.
2023-02-03 | New (in far future) | Later | Low | Pattern Library and content Library as Packed and Compressed Structure. Can have folders and subfolders, access via Treeview. (zip)
2023-02-10 | New (nice to have) | Later | Low | VU-Meter (Volume-Unit) with Peak on Voice for Note-on's sent to MidiOut. Signal-down delay up to 1.4 seconds.
2023-02-09 | Bugfix | Pending | Normal | sometimes, after some action (f.e. nudUpDown) in Voice Panel, the Track vertical scroll is set back to Position 0 (start) (when Voice and Track sroll was previous other than position 0) after moving the Voice vertical scroll, Track scroll is set back to same position as voice scroll
2023-02-10 | Improvement | Pending | Normal | Master Volume to Main Window
2023-03-03 | Bugfix | Pending | Normal | When importing special Midifiles ( Dimmu Borgir - In Death_'s Embrace.mid) some Notes sounds "deleted". We have NoteOn,NoteOn, [Duration] NoteOff,NoteOff,NoteOn,NoteOn,... Sometimes NoteOn are played before NoteOff (incorrect Sequence). NoteOns are on PlannedTime, NoteOffs are +6/+7/+8 Ticks later ???
2023-03-03 | Improvement | Pending | Normal | MidiOutList: Save NoteList as .CSV
2023-03-03 | Improvement | Pending | Normal | MidiOutList: Show Note+Velocity as hex. Add Decode Column
2023-04-13 | New (nice to have) | Later | Normal | Import from MidiFile: Split MultichannelTrack to SinglechannelTracks
|  | Pending | Normal
|  | Pending | Normal
|  | Pending | Normal
|  | Pending | Normal
|  | Pending | Normal
|  | Pending | Normal
|  | Pending | Normal
|  | Pending | Normal
|  | Pending | Normal

## Selector source
Group | Progress | Priority
| Pending | Low
Bugfix | In progress | Normal
Improvement | Finished | High
New (needed) | Later
New (nice to have)
New (in far future)